## Sprint 1 Daily SCRUM Standup
Question | Team Member | Week: 01/27/2025-02/02/2025 | [6 empty] | Week: 02/03/2025-02/09/2025 | [6 empty] | Week: 02/18/2025-02/23/2026 | [6 empty] | Week: 02/10/2025-02/17/2027
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Christian |  | 0 | 0 | 0 | 0 | Define project vision & scope | Identify system users & roles | Expand Use Case Diagram | Draft Sprint 1 Burndown Chart | Finalize Sprint 1 Backlog | Draft Sprint 1 Burndown Chart | Prepare Sprint 1 Presentation slides | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation
| Carson |  | 0 | 0 | 0 | 0 | Identify system requirements & constraints | Develop initial Context Diagram | Finalize Context Diagram | Draft Sprint 1 Burndown Chart | Review & refine Product Backlog | Draft Sprint 1 Burndown Chart | Prepare Sprint 1 Presentation slides | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation
| Jackson |  | 0 | 0 | 0 | 0 | Research security considerations | Start drafting Use Case Diagram | Review and refine requirements | Review overall progress & blockers | Check for missing system constraints | Review overall progress & blockers | Check all backlog items & documentation | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation
| Austin |  | 0 | 0 | 0 | 0 | Begin drafting team charter & roles | Outline business process improvements (BPA, BPI, BPR) | Organize initial system features | Review overall progress & blockers | Ensure use cases align with requirements | Review overall progress & blockers | Check all backlog items & documentation | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation
What will you work on today? | Christian |  |  |  |  | Define project vision & scope | Identify system users & roles | Expand Use Case Diagram | Review Use Case Diagram with team | Finalize Sprint 1 Backlog | Draft Sprint 1 Burndown Chart | Prepare Sprint 1 Presentation slides | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation | Present Sprint 1 Deliverables
| Carson |  |  |  |  | Identify system requirements & constraints | Develop initial Context Diagram | Finalize Context Diagram | Refine system requirements | Review & refine Product Backlog | Draft Sprint 1 Burndown Chart | Prepare Sprint 1 Presentation slides | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation | Present Sprint 1 Deliverables
| Jackson |  |  |  |  | Research security considerations | Start drafting Use Case Diagram | Review and refine requirements | Identify technical constraints | Check for missing system constraints | Review overall progress & blockers | Check all backlog items & documentation | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation | Present Sprint 1 Deliverables
| Austin |  |  |  |  | Begin drafting team charter & roles | Outline business process improvements (BPA, BPI, BPR) | Organize initial system features | Create draft of Product Backlog | Ensure use cases align with requirements | Review overall progress & blockers | Check all backlog items & documentation | Conduct final review of Sprint 1 work | Finalize & submit Sprint 1 documentation | Present Sprint 1 Deliverables
Do you have any obstacles? | Christian
Carson
Jackson
Austin

## Sprint 2 Daily SCRUM Standup
Question | Team Member | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday? | Christian | Reviewed SR&R 1 feedback | Identified key changes for Sprint 2 | Began updating documentation | Drafted an improved requirements list | Discussed feedback with team | Reviewed use case adjustments | Revised backlog based on feedback | Conducted initial stakeholder interviews | Gathered insights for new requirements | Began structuring non-functional requirements | - | - | - | -
| Carson | Analyzed documentation feedback | Identified missing system requirements | Conducted user interviews for feedback | Updated use case diagrams based on insights | Finalized initial backlog adjustments | Reviewed stakeholder expectations | Identified new elicitation techniques to use | Conducted additional stakeholder interviews | Refined requirement gathering approach | Worked on defining constraints for non-functional requirements | - | - | - | -
| Jackson | Reviewed security concerns raised in feedback | Researched industry best practices for security requirements | Revised security-related non-functional requirements | Collaborated with Carson on elicitation techniques | Updated documentation for security constraints | Conducted further research on security standards | Worked on refining system performance metrics | Drafted initial compliance checklist | Ensured security needs align with system requirements | Reviewed technical constraints | - | - | - | -
| Austin | Reviewed process improvements suggested in feedback | Identified key process bottlenecks | Outlined steps to incorporate feedback in business process workflows | Updated backlog with process refinements | Collaborated with Jackson on security-related process requirements | Worked on performance benchmarks for system requirements | Finalized a draft for business process documentation | Gathered additional information for non-functional requirements | Reviewed consistency across updated documents | Ensured elicited requirements align with stakeholder expectations | - | - | - | -
What will you work on today? | Christian | Incorporate final SR&R feedback into documentation | Validate changes with stakeholders | Finalize adjustments to use cases | Confirm updates align with initial project vision | Review backlog for alignment with Sprint 2 goals | Refine stakeholder feedback into actionable tasks | Ensure all updates are reflected in the backlog | Work on preparing requirements document for Sprint 2 review | Cross-check with other team members to ensure consistency | Collaborate with Carson on requirement elicitation findings | - | - | - | -
| Carson | Work on backlog refinements based on new feedback | Identify any missing use case details | Conduct follow-up interviews for additional insights | Finalize requirement elicitation strategies | Start documenting newly gathered requirements | Work on refining non-functional requirements | Ensure all elicitation findings are captured correctly | Assist with refining technical constraints | Conduct final check for missing requirements | Align all updates with team goals | - | - | - | -
| Jackson | Finalize security-related non-functional requirements | Identify system performance constraints | Review compliance considerations for security requirements | Collaborate with Austin on process alignment | Work on documenting findings for system limitations | Ensure all technical constraints are clearly defined | Finalize checklist for system performance validation | Review elicited security-related requirements | Validate system performance benchmarks | Check for consistency in all security documentation | - | - | - | -
| Austin | Refine business process improvements | Ensure alignment with technical and security requirements | Work on defining usability constraints | Collaborate with Jackson on aligning security with business workflows | Ensure all business process updates are clearly documented | Validate workflow improvements with feedback received | Ensure non-functional requirements cover all key constraints | Finalize documentation for process enhancements | Conduct final quality check | Review all updates with stakeholders for sign-off | - | - | - | -
Do you have any obstacles? | Christian | Need clarification on some feedback points | Unclear priorities in feedback | Ensuring backlog updates align with team objectives | Stakeholder availability for validation meetings | Time constraints in finalizing documentation | - | - | - | - | - | - | - | - | -
| Carson | Some requirements are vague or incomplete | Difficulty scheduling stakeholder meetings | Ensuring requirement elicitation is thorough enough | Balancing requirement gathering with documentation | Managing workload with other Sprint 2 tasks | - | - | - | - | - | - | - | - | -
| Jackson | Security requirements are complex and evolving | Compliance regulations require more research | Ensuring all security concerns are captured accurately | Aligning technical constraints with system capabilities | Balancing security with usability in non-functional requirements | - | - | - | - | - | - | - | - | -
| Austin | Some process refinements require additional data | Ensuring usability constraints are well-defined | Making sure process changes don't conflict with security | Documenting workflow improvements effectively | Balancing multiple refinement tasks | - | - | - | - | - | - | - | - | -

## Sprint 3 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 4 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 5 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Sprint 6 Daily SCRUM Standup
Question | Team Member | Week: xx/xx/202x-xx/xx/202x | [6 empty] | Week: xx/xx/202x-xx/xx/202x
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
What did you do yesterday?
What will you work on today?
Do you have any obstacles?