## SYSTEM PRODUCT BACKLOG
PROJECT PRODUCT BACKLOG |  |  |  | Assignment |  | STATUS KEY
UR# | Item | Priority | Status | Team Member | Sprint | OPEN
1 | Define Project Scope and Objectives | High | Completed | Austin | 1 | CLOSED
2 | Identify Systems Requirements | High | Completed | Carson | 1
3 | Develop Context Diagram & Use Case Diagram | High | Completed | Christian | 1
4 | Identify Key System Users | Medium | Completed | Jackson | 1
5 | Research Potential Security Risks | Medium | Completed | Jackson | 1
6 | Design the ERD | High | OPEN | Jackson | 2
7 | Create Database Schema | High | OPEN | Christian | 2
8 | Implement User Authentication | High | OPEN | Austin | 2
9 | Optimize Query Performance & Indexing | Medium | OPEN | Carson | 2
10 | Develop Homepage | High | OPEN | Austin | 3
11 | Create Customer Registration | High | OPEN | Jackson | 3
12 | Implement Request a Quote form | Low | OPEN | Carson | 3
13 | Design Dashboard | Medium | OPEN | Austin | 3
14 | Ensure Mobile Responsiveness | Low | OPEN | Christian | 3
15 | Develop Customer Retrieval System | High | OPEN | Jackson | 4
16 | Implement Pricing Calculation | Medium | OPEN | Austin | 4
17 | Set up automated email confirmations | Low | OPEN | Carson | 4
18 | Develop logging system for errors | Low | OPEN | Christian | 4
19 | Conduct unit testing on database & frontend | High | OPEN | Jackson | 5
20 | Deploy system to live server | High | OPEN | Carson | 5
21 | Monitor and Resolve Deployment Issues | High | OPEN | Austin | 5
22 | Create user manual | High | OPEN | Christian | 5
23 | Develop training materials | High | OPEN | Austin | 6
24 | Develop System Architecture | High | OPEN | Jackson | 6
25 | Conduct Training Sessions | High | OPEN | Carson | 6
26 |  |  | OPEN
27 |  |  | OPEN
28 |  |  | OPEN
29 |  |  | OPEN
30 |  |  | OPEN
31 |  |  | OPEN
32 |  |  | OPEN
33 |  |  | OPEN
34 |  |  | OPEN
35 |  |  | OPEN
36 |  |  | OPEN
37 |  |  | OPEN
38 |  |  | OPEN
39 |  |  | OPEN
40 |  |  | OPEN
41 |  |  | OPEN
42 |  |  | OPEN
43 |  |  | OPEN
44 |  |  | OPEN
45 |  |  | OPEN
46 |  |  | OPEN
47 |  |  | OPEN
48 |  |  | OPEN
49 |  |  | OPEN
50 |  |  | OPEN

## SPRINT 1 BACKLOG
SPRINT 1 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
1 | Define Project Scope and Objectives | High | Completed | Austin | CLOSED
2 | Identify Systems Requirements | High | Completed | Carson
3 | Develop Context Diagram & Use Case Diagram | High | Completed | Christian
4 | Identify Key System Users | Medium | Completed | Jackson
5 | Research Potential Security Risks | Medium | Completed | Jackson

## SPRINT 2 BACKLOG
SPRINT 2 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED

## SPRINT 3 BACKLOG
SPRINT 3 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED

## SPRINT 4 BACKLOG
SPRINT 4 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED

## SPRINT 5 BACKLOG
SPRINT 5 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED

## SPRINT 6 BACKLOG
SPRINT 6 BACKLOG |  |  |  | Assignment | STATUS KEY
UR# | Item | Priority | Status | Team Member | OPEN
CLOSED