## Sprint 1 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
1 | Define Project Scope and Objectives | [15 empty] | Jackson
2 | Identify Systems Requirements | [15 empty] | Austin
3 | Develop Context Diagram & Use Case Diagram | [15 empty] | Christian
4 | Identify Key System Users | [15 empty] | Carson
5 | Research Potential Security Risks | [16 empty] | 0 | Total Team Time
Remaining Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sprint 2 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
6 | Incorporate Feedback | 3 | [14 empty] | Jackson | 5 | bar: Day 1 to Day 3
7 | Design the Entity-Relationship Diagram | 3 | Day 4: 1; Day 5: 2 | Austin | 5
8 | Create Database Schema | 4 | Day 6: 2; Day 7: 2 | Christian | 7
9 | Design User Authentication | 4 | Day 8: 1; Day 9: 1; Day 10: 2 | Carson | 4
10 | Update Diagrams | 2 | Day 11: 2 |  | 21 | Total Team Time
11 | Design & Document Non-Functional Requirements | 3 | Day 12: 1; Day 13: 2
12 | Develop Sprint 2 Burndown Chart & Backlog | 2 | Day 14: 2
Remaining Effort |  | 21 | 20 | 19 | 18 | 17 | 15 | 13 | 11 | 10 | 9 | 7 | 5 | 4 | 2 | 0
Ideal Effort |  | 21 | 19.5 | 18 | 16.5 | 15 | 13.5 | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0

## Sprint 3 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
13 | Incorporate Feedback | 3 | [21 empty] | Jackson | 5 | bar: Day 1 to Day 3
14 | Develop Homepage | 2 | [21 empty] | Austin | 6 | bar: Day 4 to Day 5
15 | Create Customer Registration | 2 | Day 6: 0; Day 7: 2 | Christian | 5
16 | Create DFD's Level 0 & 1 | 4 | Day 8: 3; Day 9: 1; Day 10: 0; Day 11: 0 | Carson | 5
17 | Design Dashboard | 1 | [22 empty] | 21 | Total Team Time | bar: Day 12
18 | Design Program Plan (IPO) | 4 | Day 13: 2; Day 14: 0; Day 15: 2; Day 16: 0
19 | Develop Navigation Diagram | 3 | Day 17: 1; Day 18: 2
20 | Design Error Handling | 2 | bar: Day 19 to Day 20
21 | Create Sprint 3 Burndown Chart & Backlogs | 2 | Day 20: 1; Day 21: 2
Remaining Effort |  | 23 | 22 | 21 | 20 | 19 | 18 | 18 | 16 | 13 | 12 | 12 | 12 | 11 | 9 | 9 | 7 | 7 | 6 | 4 | 3 | 1 | -1
Ideal Effort |  | 23 | 21.9048 | 20.8095 | 19.7143 | 18.619 | 17.5238 | 16.4286 | 15.3333 | 14.2381 | 13.1429 | 12.0476 | 10.9524 | 9.8571 | 8.7619 | 7.6667 | 6.5714 | 5.4762 | 4.381 | 3.2857 | 2.1905 | 1.0952 | 5.3291e-15

## Sprint 4 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Team Member | Total Time
22 | Incorporate Feedback | 3 | [21 empty] | Jackson | 8 | bar: Day 1 to Day 3
23 | Develop Customer Retrieval System | 4 | Day 4: 2; Day 5: 2 | Austin | 6
24 | Implement Pricing Calculation | 4 | Day 6: 1; Day 7: 1; Day 8: 2 | Christian | 8
25 | Develop Training Manual | 7 | Day 9: 2; Day 10: 2; Day 11: 2; Day 12: 1 | Carson | 7
26 | Create Technical Documentation | 7 | Day 13: 2; Day 14: 2; Day 15: 1; Day 16: 1; Day 17: 1 |  | 29 | Total Team Time
27 | Plan User Training | 2 | bar: Day 18 to Day 19
28 | Finalize Sprint 4 Burndown Chart & Backlog | 2 | bar: Day 20 to Day 21
Remaining Effort |  | 29 | 28 | 27 | 26 | 24 | 22 | 21 | 20 | 18 | 16 | 14 | 12 | 11 | 9 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Ideal Effort |  | 29 | 27.619 | 26.2381 | 24.8571 | 23.4762 | 22.0952 | 20.7143 | 19.3333 | 17.9524 | 16.5714 | 15.1905 | 13.8095 | 12.4286 | 11.0476 | 9.6667 | 8.2857 | 6.9048 | 5.5238 | 4.1429 | 2.7619 | 1.381 | 8.4377e-15

## Sprint 5 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
29 | Incorporate Feedback | 4 | Day 1: 2; Day 2: 2 | Jackson | 9
30 | Conduct unit testing on database & frontend | 3 | Day 3: 1; Day 4: 2 | Austin | 2
31 | Deploy system to live server | 5 | Day 5: 1; Day 6: 2; Day 7: 2 | Christian | 4
32 | Monitor and Resolve Deployment Issues | 2 | Day 8: 2 | Carson | 11
33 | Create user manual | 4 | Day 9: 2; Day 10: 2 |  | 26 | Total Team Time
34 | Develop Migration Plan | 6 | Day 11: 2; Day 12: 2; Day 13: 2
35 | Create Sprint 5 Burndown Chart & Backlog | 2 | Day 14: 2
Remaining Effort |  | 26 | 24 | 22 | 21 | 19 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
Ideal Effort |  | 26 | 24.1429 | 22.2857 | 20.4286 | 18.5714 | 16.7143 | 14.8571 | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | -5.7732e-15

## Sprint 6 Burndown
Backlog Item ID | User Stories / Requirements / Bugs | Estimated Time | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Team Member | Total Time
36 | Incorporate Feedback | 2 | Day 1: 2 | Jackson | 12
37 | Develop training materials | 3 | Day 2: 1; Day 3: 2 | Austin | 1
38 | Develop System Architecture | 4 | Day 4: 2; Day 5: 2 | Christian | 1
39 | Conduct Training Sessions | 4 | Day 6: 2; Day 7: 2 | Carson | 12
40 | Finalize Technical Documentation | 3 | Day 8: 1; Day 9: 2 |  | 26 | Total Team Time
41 | Prepare & Present Final Project Demo | 4 | Day 10: 2; Day 11: 2
42 | Submit Final Project Documentation | 4 | Day 12: 2; Day 13: 2 |  | Total Project Time
43 | Create Sprint 6 Burndown Chart & Backlog | 2 | Day 14: 2 |  | Sprint 1 | 20
[18 empty] | Sprint 2 | 21
[18 empty] | Sprint 3 | 21
[18 empty] | Sprint 4 | 29
[18 empty] | Sprint 5 | 26
[18 empty] | Sprint 6 | 26
[19 empty] | 143 | Total Project Time
Remaining Effort |  | 26 | 24 | 23 | 21 | 19 | 17 | 15 | 13 | 12 | 10 | 8 | 6 | 4 | 2 | 0
Ideal Effort |  | 26 | 24.1429 | 22.2857 | 20.4286 | 18.5714 | 16.7143 | 14.8571 | 13 | 11.1429 | 9.2857 | 7.4286 | 5.5714 | 3.7143 | 1.8571 | -5.7732e-15